## CRITICAL PATH - OVERVIEW Blank
CRITICAL PATH ( WORK IN PROGRESS ) |  |  |  |  | BUSINESS : |  |  | SEASON : |  |  |  | DATE UPDATED:
OVERVIEW | [8 empty] | PRODUCTION |  |  |  |  | LAB DIP/STRIKE OFF STATUS |  | FIT STATUS |  |  | FABRIC STATUS |  |  | TRIM STATUS |  |  | BRANDING |  | PRODUCTION STATUS |  |  | notes:
Drop | Style description | style no. | Purchase order no. | Fabric | color | wash/finish | delivery date | Units | Price (FOB) | RRP | Local/Import | Mode (air/sea) | Factory | date sent | date app | Toile | proto sample | app date | testing | dispatched | in-house | testing to fabric | approved | in house | approved | in house | cut | sewn | wash/finish

## CRITICAL PATH - OVERVIEW dept.
CRITICAL PATH ( WORK IN PROGRESS ) |  |  |  |  | BUSINESS : |  |  | SEASON : |  |  |  | DATE UPDATED:
OVERVIEW | [8 empty] | PRODUCTION |  |  |  |  | LAB DIP/STRIKE OFF STATUS |  | FIT STATUS |  |  | FABRIC STATUS |  |  | TRIM STATUS |  |  | BRANDING |  | PRODUCTION STATUS |  |  | notes:
Drop | Style description | style no. | Purchase order no. | Fabric | color | wash/finish | delivery date | Units | Price (FOB) | RRP | Local/Import | Mode (air/sea) | Factory | date sent | date app | Toile | proto sample | app date | testing | dispatched | in-house | testing to fabric | approved | in house | approved | in house | cut | sewn | wash/finish
The critical path is a key component of the Advanced diploma course and must be used across all subjects. This will be introducted in the production cluster and carried as a print out by the students to fill in across all subjects, they may need to create
several blank critical paths, and keep every update . Every time a student meets with a trainer this should be with them.
KEY to responsibilities in each area: |  |  | DESIGN | PATTERNS | PRODUCTION

## example of Import tracking
THIS IS A BASIC EXAMPLE TO SHOW STUDENTS OF AN INTUSTRY IMPORTING CIRITCAL PATH - some times reftered to as Tracking or Production plan
SUMMER 2012 - TRACKING
No | STYLE / PO | PHOTO | DESCRIPTION | FABRIC/TRIMS | WASH / COLOUR | BLOCK | SUPPLIER | DATE SENT | SUPPLIER REC | SUPPLIER SENT | NOTES:
| YOUR STYLE NUMBER OR PURCHASE ORDER NUMBER | ORIGNAL GARMENT OR TRADE SKETCH | OF GARMENT i.e. SKINNY LEG JEAN and garment name if applicable | Fabric / trim code , composition, width , etch | list colours and or wash technique | if applicable, refers to the Pattern - this is a reference for the shape. | Suppliers name | date first inforamtion pack was sent to request a proto sample | supplier to fill in | date supplier send proto sample etc
General example of PRODUCTION tracking - So from orders / Commitment placed
No | STYLE / PO | PHOTO | DESCRIPTION | FABRIC/TRIMS | WASH / COLOUR | SUPPLIER | TECH PACK SENT | FABRIC BOOKED | ARTWORK SENT | FIT APPROVED | LABELS APPROVED | STRIKE OFF APPROVAL | LAB DIPS APPROVED
[5 empty] | A) SAND - as men's B) BLACK ACID as 6515430 Charlatan | EDWARD WONG | USUALLY 3 MONTHS BEFORE DELIVERY OR AS FAST AS 6 WEEKS | GREIGE LEAD TIME CAN BE UP TO 90 DAYS | ALLOW 14 -21 DAYS FOR STRIKE OFF | ALLOW 5 DAYS TO FIT AND APPROVE
Cont. From Lab dips
| TRIMS APPROVED | ROAD /SALES SAMPLE APPROVED | BULK FABRIC APPROVED | PP SAMPLE APPROVED | 2ND PP SAMPLE APPROVED | Q.C REPORT | BULK APPROVED | HAND OVER DATE | AIR FREIGHT | SEA FREIGHT | LANDED DATE | DELIVERED TO D.C. | CUSTOMER DELIVERY
|  | ALLOW 5 DAYS TO FIT AND APPROVE |  | ALLOW 5 DAYS TO FIT AND APPROVE | ALLOW 5 DAYS TO FIT AND APPROVE | DELIVERED TO D.C. | ALLOW 5 DAYS TO FIT AND APPROVE | 24 HOURS - 2 DAYS BEFORE DATE ON VESSLE / FLIGHT | 7 - 10 DAYS | 6 - 8 WEEKS | NORMALLY ALLOW 2 WEEKS FROM DELIVERY | 3-4 DAYS TO PROCESS / PICK AND PACK | CUSTOMER DELIVERY
P.P = PURCHASE ORDER - A Purchase order is generated normally once a price and units are confirmed with a supplier
Other definitions needed
MOQ = Minimum order quantiy
LEAD TIEMS = time it take for a factory to produce the goods once they have approval
COMPACITY = Space/Time available in factories
FOB = Freight on Borad ( total make price of a style but not including shipping )
CMT = Cut make trim ( not including fabric or shipping )
AIR FREIGHT = Sending goods by Air ( usually 7 -10 Days lead time Door to Door )
SEA FREIGHT = Sending goods by SHIP ( can take up to 6 weeks , faster times can be done )
FREIGHT FORWARDER = company who will co-ordinate all freight, from hand over of a supplier to
delivery into warehouse
CLEARING AGENT = will be respoinsible for working with customs to get ' CUSTOMS CLEARANCE '